## Sheet1
SEO Plan for Jim Green
Beginning budget: | 1000
Hourly Wages:
Executive Manager | 35
In-house Manager | 19
Copywriter | 15
Copywriter Intern | 8.75
Developer | 15
Developer Intern | 8.75
Graphic Designer | 15
Graphic Designer Intern | 8.75
Advertiser | 15
Advertiser Intern | 8.75
General notes: | 1) Phases II and III can run concurrently
2) Phases IV and V can run concurrently
3) All time is quoted in hours
Phase I: Brainstorming Meeting with all managers and employees
Meeting Length: | 1.5
Budget consumed: | 223.5
Budget remaining: | 776.5
Phase II: Copywriter and intern write the content for the site
Copywriter Time: | 5
Coypwriter Intern Time: | 5
In House Mgr Time: | 0.5
Budget consumed: | 128.25
Budget remaining: | 648.25
Phase III: Graphic Designer and intern work on site design
Graphic Designer Time: | 5
Graphic Designer Intern Time: | 5
In House Mgr Time: | 0.5
Budget consumed: | 128.25
Budget remaining: | 520
Phase IV: Developer and intern code web pages and upload content to server.
Developer Time: | 4
Developer Intern Time: | 4
In House Mgr Time: | 0.5
Budget consumed: | 104.5
Budget remaining: | 415.5
Phase V: Advertiser and intern write meta tag descriptions and PPC ads.
Advertiser Time: | 3
Advertiser Intern Time: | 3
In House Mgr Time: | 0.5
Budget consumed: | 80.75
Budget remaining: | 334.75
Phase VI: Debrief with all managers and employees
Estimated Time (hours) | 1
Budget consumed | 149
Budget Remaining | 185.75
Summary of Project Expenses
Employee | Hours | Wage
Executive Manager | 2.5 | 87.5
In House Manager | 4.5 | 85.5
Copywriter | 7.5 | 112.5
Copywriter Intern | 7.5 | 65.625
Developer | 6.5 | 97.5
Developer Intern | 6.5 | 56.875
Graphic Designer | 7.5 | 112.5
Graphic Designer Intern | 7.5 | 65.625
Advertiser | 5.5 | 82.5
Advertiser Intern | 5.5 | 48.125
Total Hours | 61
Total Wages | 814.25
Budget Remaining | 185.75